## Tsunamis
Tsunamis Statement of Work
| Project Title |  | Start Date
| Help Desk |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Eric (Lead), Jayce (Tester), Tre'sure (SWE), no Designer |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Eric |  |  | 2025-11-11 | 2025-12-08 | 28 |  | Not Started
| # Update README with prioritized projects | On Hold | SHA b6fa387 | 2025-11-11 | 2025-11-11 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
Complete
On Hold
Nov 26th: 5 commits, +616, -2
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Jayce |  |  | 2025-11-20 | 2025-12-08 | 19
| #3. Create initial driver and Scraper class to scrape (unprocessed) academic calendar | Complete | SHA 9eaf8aa | 2025-11-20 | 2025-11-20 | 1
| #3a-e. Create function that returns the drop dates for each semester | Complete | SHA 2b67803, d259f2b | 2025-11-21 | 2025-11-21 | 1
| #3f. Create test for functions in PerformScraping.py | Complete | SHA 715e50c, cbcede1, 7d24d14, c449c6f, 91dc76b, 4009e4d | 2025-11-23 | 2025-11-23 | 1
| #5e. Test resources.py | Complete | SHA ef8e7cc, 91ecc54, 1c3a8a5, 72fd372, e155579, fc7bd08 | 2025-12-01 | 2025-12-01 | 1
| #5e. Test every resources link to ensure nothing is broken | Complete | SHA c962f98, d3153c0 | 2025-12-01 | 2025-12-01 | 1
| #6h. Create tests for drop slip class | Complete | SHA 327df74, 721c5cd, 8d15cfc, d0b2b22, 971b233, 917d06b, | 2025-12-01 | 2025-12-01 | 1
| #6i. Create tests for schedule class | Complete | SHA 4decf9d | 2025-12-01 | 2025-12-01 | 1 | I had more commits for this use case, but I had an issue merging the branch after the test fiolder was added.
| #Update checklist for team member contributions | Complete | SHA 7e8229d | 2025-12-01 | 2025-12-01 | 1
Nov 26th: 9 commits, +176, -15
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Tre'sure |  |  | 2025-11-12 | 2025-12-08 | 27
| # Create Course data class (strangely your data class includes 2 functions that should be in the Course class), also called in the driver | On Hold | SHA e45fb67, 064665a, 62aa1ef | 2025-11-12 | 2025-11-14 | 3 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | You and Eric need to figure out why Jayce is listed as a Contributor on our shared repo but tresurent is not. Tre'sure can't earn points on this assignment unless she is a contributor to our shared repo.
Nov 26th: 36 commits, +337, -250
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Vacant |  |  | 0 | 0 | 0
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL