## Tsunamis
Tsunamis Statement of Work
| Project Title |  | Start Date
| Help Desk |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Eric (Lead), Jayce (Tester), Tre'sure (SWE), no Designer |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments
| Eric |  |  | 2025-11-11 | 2025-12-08 | 28
README | # Update README with prioritized projects | On Hold | SHA b6fa387 | 2025-11-11 | 2025-11-11 | 1
| #Course Offering User Story | Complete | SHA 215af22 | 2025-11-11 | 2025-11-29
convert_grade_to_points(), calculate_gpa(), run_gpa_calculator() test_single_course_gpa(), test_multiple_courses_gpa(), test_invalid_grade_raises(), test_missing_credit_hours_raises(), test_zero_total_hours_raises(), test_mismatched_list_lengths_raises() check README | #GPA Calculator User Story | Complete | SHA 620f505 ,fbf1d88 ,090a8ae, c3b5e05 | 2025-11-11 | 2025-11-21
| #Project Maintenance (SDD, README, tests folder) | Complete | SHA 7a59184 | 2025-11-22 | 2025-12-01
driver.py (main, shw_drop_datesrun_course_offering_check) | #Install & configure requests + bs4 | Complete | SHA a88abe2 | 2025-11-22 | 2025-11-29
| #Fix/organize test folder for test discovery | Complete | SHA 266c6647, a98aef9, a277a4 | 2025-11-20 | 2025-12-01
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Jayce |  |  | 2025-11-20 | 2025-12-08 | 19
Scraper (getAcademicCalander) and call in main() | Create initial driver and Scraper class to scrape (unprocessed) academic calendar | Complete | SHA 9eaf8aa | 2025-11-20 | 2025-11-20 | 1
getDropDates() and call in main(), edit main() | Create function that returns the drop dates for each semester | Complete | SHA 2b67803, d259f2b | 2025-11-21 | 2025-11-21 | 1
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
ScraperTest() using mocks, test_getAcademicCalander_no_url_provided(), test_getAcademicCalander_invalid_url() test_get_Drop_Dates_succes(), test_getDropDates_invalid_rows() | Create test for functions in PerformScraping.py | Complete | SHA 715e50c, cbcede1, 7d24d14, c449c6f, 91dc76b, 4009e4d | 2025-11-23 | 2025-11-23 | 1
test_returns_list(), test_resource_count(), test_items_are_resources() | Test resources.py | Complete | SHA ef8e7cc, 91ecc54, 1c3a8a5, 72fd372, e155579, fc7bd08 | 2025-12-01 | 2025-12-01 | 1
link_requests(), test_functional_links(), test_nonfunctional_links() | Test every resources link to ensure nothing is broken | Complete | SHA c962f98, d3153c0 | 2025-12-01 | 2025-12-01 | 1
test_to_text(), test_to_text_empty_fields(), test_write_drop_slip_to_file() | Create tests for drop slip class | Complete | SHA 327df74, 721c5cd, 8d15cfc, d0b2b22, 971b233, 917d06b, | 2025-12-01 | 2025-12-01 | 1
test_add_course(), test_is_registered(), test_is_registered_false(), test_load_course_from_csv_course_found(), test_load_course_from_csv_course_not_found() | Create tests for schedule class | Complete | SHA 4decf9d | 2025-12-01 | 2025-12-01 | 1 | I had more commits for this use case, but I had an issue merging the branch after the test fiolder was added.
check | Update checklist for team member contributions | Complete | SHA 7e8229d | 2025-12-01 | 2025-12-01 | 1
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Tre'sure |  |  | 2025-11-12 | 2025-12-08 | 27
Course load_courses(), filter_by_subject(), prompt_subject(), show_course_list(), select_course(), show_course_details(), run_crn_lookup() data/courses.csv main() | Create Course data class (strangely your data class includes 2 functions that should be in the Course class), also called in the driver | Complete | SHA e45fb67, 064665a, 62aa1ef | 2025-11-12 | 2025-11-14 | 3 | SHA e45fbb67. The SHA was supposed to contain a data/couses.csv file. However it is blank. That particular push created the file but did not upload the given data. The csv file was made to contain example courses for our application to pull from. The original SHA that was given was in error. Instead of double checking, I left the SHA that was already there, which was incorrect. At the time, I did not see that the SHA was blank. SHA 62aa1ef. This was originally a driver that I was using for my original code for the crn_check.py file. At the start of the project, I thought it was best to keep everything separate for the sake of organization , but after one of our team meetings, I realized that since we needed to run our code from one command, my driver was not only irrelevant , but would also mess up the code. It was originally in the SOW due to the fact that it was the first code for that case , but upon changing it, the SHA should have been removed and replaced with the one listed below.
only white space | #1 1(a)The student types the subject in the search bar. 1(b)The page displays a scrollable list of courses for that subject. 1(c)The student clicks on the desired course. 1(d)The student clicks on the desired course. 1(e)The card displays the course description, CRN, prerequisites, and the add deadline. 1(f)Implement a function that reads course data from a CSV/JSON file. 1(g)Implement a search function that filters courses by a subject code and returns them sorted by course number. 1(h)Implement a "view_details" function that , given a selected, prints and shows the desciption, CRN, prerequisites, and add/drop dates. 1(i)Verify that entering a invalid input will show a "No courses found" message instead of ending the code. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3 | Dr. Edwards got User Story # from Trello.
copied from Line 29 | 1(i)Verify that entering a invalid input will show a "No courses found" message instead of ending the code. | Complete | SHA 4f6dff, ffeadef, | 2025-11-23 | 2025-11-26 | 3 | SHA ffeadef. The data from my previous SRC file was transferred to data/courses.csv which contains the data used to run the application for our code. This is the corrected SHA which shows the code that I created to implement my work into the driver. SHA 4f6dff1 or ffeadef. I was trying to show my corrected crn_check.py code and instead the push was empty. Although I am not sure why, is was a mistake on my end and I have sent the correct SHA below. The commit was meant to show a clean, working code for Use Case 1. It was intended to include the code and the functions implemented in the driver. SHA 4f6dff1 or 127108b. This SHA was supposed to add in the testing code so that if could verify and produce a “Invalid Input” message. As stated earlier, the SHA was empty and blank. I have attached the correct test SHA below.
TestCrnCheck |  | Complete | SHA 127108b | 2025-11-26 | 2025-11-26 | 2 | SHA 4f6dff1 or 12718b. This SHA was supposed to add in the testing code so that if could verify and produce a “Invalid Input” message. As stated earlier, the SHA was empty and blank. I have attached the correct test SHA below.
file renamed DropSlip (__init__, to_text, write_drop_slip_to_file) Schedule (__init__, add_course, is_registered) load_course_from_csv() called create_drop_slip | 6(a)CreAte a schedule class. 6(b)Create a drop slip class. 6(c)Create a function that writes to a drop slip file. 6(d)Retrieve the CRN and all other necessary information for a course. 6(e)]Check if the student is registered for the course. 6(f)The app prompts the user to enter the course that they wish to drop. | Complete | SHA 8e4d561, 9ec9ea1, 3e514a0, 7ef6f19 | 2025-11-29 | 2025-11-29 | 1
validate_course_code() | 4(d)Validate course code input: ensure the input is not empty and follows a pattern like SUBJECT + NUMBER. | Complete | SHA abe82b5 | 2025-11-29 | 2025-11-30 | 2
find_sections_for_code() | 4(e)]Implement search function that takes the course code and checks the current semester’s course offerings. | Complete | SHA 41bb0ed | 2025-11-29 | 2025-11-30 | 2
check_course_availability() | 4(f) Display results for offered course: show “Course is offered this semester” and list all matching sections (CRN, days/times, instructor, seats). 4(g)Display message for not offered / not found course: show a clear message when no matching course exists for the semester. 4(h)Handle “all sections full” case: when course is offered but has no open seats, show a message like “All sections are full.” | Complete | SHA 612067d | 2025-11-29 | 2025-11-30 | 2
Resource load_default_resources() | 5(b)Build a resources module with URLs, icons, and categories. | Complete | SHA 8e0ad41 | 2025-11-29 | 2025-11-30 | 2
show_resources_menu() | 5(a)Show quick-link resources so I don’t have to search XULA’s website. | Complete | SHA cd55f92 | 2025-11-29 | 2025-11-30 | 2
handle_resource_selection() get_drop_deadline_info() | 5(c)Click “Drop Deadline Calendar” and see the dates instantly. | Complete | SHA d6d3fdc | 2025-11-29 | 2025-11-30 | 2
show_professor_contacts() load_professor_contacts() | 5(f)Make professor office hours and emails displayed for common CPSC courses. | Complete | SHA e4b6a80 | 2025-11-29 | 2025-11-30 | 2
resources.json() load_resources_from_json() | 5(j)Store the resources in a JSON or CSV file so they’re easy to update later. | Complete | SHA 6a2774e | 2025-11-29 | 2025-11-30 | 2
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F16)
End Date = MAX([End Date, row below]:G16)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL